## Progress Tracker
ID | Research Module | Task | Priority | Owner | Start Date | Due Date | Status | % Complete | Evidence Link | Risks/Blockers | Next Action
1 | Foundation | Approve this master blueprint | High | Founder |  |  | Not Started | 0% |  | Leadership availability | Schedule review meeting
2 | Foundation | Set up research repository (folder structure) | High | Ops |  |  | Complete | 100% | research/ (folder tree live) |  | None — maintain as new modules are added
3 | Foundation | Assign module owners | High | Founder |  |  | In Progress | 50% | 01-Foundation/RACI.md | Roles proposed by task-fit; real names still need founder confirmation | Founder confirms names against proposed roles in RACI.md
4 | Foundation | Set up progress tracker in project tool | Medium | Ops |  |  | In Progress | 60% | Nivy_Next_Progress_Tracker.xlsx (live, this file) | Working in Excel, not yet migrated to a shared project tool (Notion suggested in Dashboard_Tool_Spec.md) | Decide whether to migrate tracker into Notion alongside the rest of Nivy Empires workspace
5 | Market Intelligence | Build USA country snapshot | High | Research | 2026-08-06 | 2026-08-06 | Complete | 100% | 02-Market-Intelligence/Country-Snapshots/ |  | Move to competitor benchmarking (Task 10)
6 | Market Intelligence | Build Canada country snapshot | High | Research | 2026-08-06 | 2026-08-06 | Complete | 100% | 02-Market-Intelligence/Country-Snapshots/ |  | Move to competitor benchmarking (Task 10)
7 | Market Intelligence | Build UK country snapshot | High | Research | 2026-08-06 | 2026-08-06 | Complete | 100% | 02-Market-Intelligence/Country-Snapshots/ |  | Move to competitor benchmarking (Task 10)
8 | Market Intelligence | Build Australia country snapshot | High | Research | 2026-08-06 | 2026-08-06 | Complete | 100% | 02-Market-Intelligence/Country-Snapshots/ |  | Move to competitor benchmarking (Task 10)
9 | Market Intelligence | Build UAE country snapshot | High | Research | 2026-08-06 | 2026-08-06 | Complete | 100% | 02-Market-Intelligence/Country-Snapshots/ |  | Move to competitor benchmarking (Task 10)
10 | Market Intelligence | Identify top 5 direct competitors | High | Research | 2026-08-06 | 2026-08-06 | Complete | 95% | 02-Market-Intelligence/Competitor-Benchmarking/Competitor_Data_Collection_Master.md | All 5 competitors now have a pricing signal from direct site checks. Likely name correction found: "Z Rankings" appears to actually be EZ Rankings (near-identical published stats/services) — EZ Rankings has full published SEO pricing ($225-$1,099/mo). Eminenture and Fusion/FBSPL both confirmed quote-only on their own sites but have matching Clutch aggregate bands ($1,000+ min, <$25/hr). | Founder/researcher to confirm the Z Rankings = EZ Rankings identity against original source material before treating as final; otherwise pricing picture is essentially complete for desk research
11 | Market Intelligence | Complete competitor benchmark matrix | High | Research | 2026-08-06 | 2026-08-06 | In Progress | 95% | 02-Market-Intelligence/Competitor-Benchmarking/Competitor_and_Market_Pricing_Benchmark_v1.md | Benchmark now includes real published pricing for EZ Rankings (likely = former "Z Rankings" entry) showing a much lower market floor ($225/mo) than previously known — sharpens the low-cost-lane vs premium-lane positioning decision in Deliverable 4.4 | Founder review updated benchmark, especially the EZ Rankings $225/mo floor and its implication for Digital Marketing Starter tier pricing
12 | Market Intelligence | Run SWOT on top 3 competitors | Medium | Research | 2026-08-06 | 2026-08-06 | Complete | 100% | 02-Market-Intelligence/Competitor-Benchmarking/SWOT_Top3_Competitors_v1.md |  | Revisit quarterly via shift report
13 | Market Intelligence | Industry prioritization scoring | High | Research | 2026-08-06 | 2026-08-06 | Complete | 100% | 02-Market-Intelligence/Industry_Prioritization_Scoring_v1.md |  | Feeds ICP card prioritization (Tasks 14-21)
14 | ICP Research | Draft ICP cards — Accounting-adjacent/ops angle | Medium | Sales | 2026-08-06 | 2026-08-06 | In Progress | 60% | 03-ICP-Buyer-Research/ICP-Cards/ICP_AccountingAdjacentOps_SMB.md | Hypothesis-stage — needs VoC validation; also depends on Trust & Compliance drafts before leading with it in outreach | Validate via VoC interviews; do not lead outreach with this ICP until Tasks 46-49 legal-reviewed
15 | ICP Research | Draft ICP cards — Digital Marketing | High | Sales | 2026-08-06 | 2026-08-06 | In Progress | 60% | 03-ICP-Buyer-Research/ICP-Cards/ICP_DigitalMarketing_SaaS-Tech.md | Hypothesis-stage — needs VoC validation | Validate via 5+ SaaS-segment VoC interviews
16 | ICP Research | Draft ICP cards — IT Services | High | Sales | 2026-08-06 | 2026-08-06 | In Progress | 60% | 03-ICP-Buyer-Research/ICP-Cards/ICP_ITServices_ProfessionalServices.md | Hypothesis-stage — needs VoC validation | Validate via 5+ professional-services VoC interviews
17 | ICP Research | Draft ICP cards — AI & Automation | High | Sales | 2026-08-06 | 2026-08-06 | In Progress | 60% | 03-ICP-Buyer-Research/ICP-Cards/ICP_AIAutomation_Ecommerce.md | Hypothesis-stage — needs VoC validation | Validate via 5+ e-commerce/DTC VoC interviews
18 | ICP Research | Draft ICP cards — Web Development | High | Sales | 2026-08-06 | 2026-08-06 | In Progress | 60% | 03-ICP-Buyer-Research/ICP-Cards/ICP_WebDevelopment_SaaS-ProfessionalServices.md | Hypothesis-stage — needs VoC validation | Validate via VoC interviews
19 | ICP Research | Draft ICP cards — Virtual Assistant Services | Medium | Sales | 2026-08-06 | 2026-08-06 | In Progress | 60% | 03-ICP-Buyer-Research/ICP-Cards/ICP_VirtualAssistant_Founders.md | Hypothesis-stage — needs VoC validation | Validate via VoC interviews
20 | ICP Research | Draft ICP cards — Graphic Design | Medium | Sales | 2026-08-06 | 2026-08-06 | In Progress | 60% | 03-ICP-Buyer-Research/ICP-Cards/ICP_GraphicDesign_Ecommerce.md | Hypothesis-stage — needs VoC validation | Validate via VoC interviews
21 | ICP Research | Draft ICP cards — Video Editing | Medium | Sales | 2026-08-06 | 2026-08-06 | In Progress | 60% | 03-ICP-Buyer-Research/ICP-Cards/ICP_VideoEditing_DTC-SaaS.md | Hypothesis-stage — needs VoC validation | Validate via VoC interviews
22 | VoC Research | Interview 5 current happy clients | High | Founder |  |  | Not Started | 0% | 03-ICP-Buyer-Research/VoC-Interviews/20260806_Secondary_VoC_Research_PublicReviews_v1.md; 20260806_Secondary_VoC_Research_SMBSurveyData_v1.md | Question bank ready — needs contact list + scheduling. Interim: 2 secondary-research passes complete (Clutch/G2/Trustpilot + SMB survey data) as a stand-in per Bridge Plan Part 1 | Pull first 10 contacts from CRM/network (5 current or ICP-fit contacts + 5 lost prospects) and send invites; target 8-10 non-customer ICP conversations per Bridge Plan
23 | VoC Research | Interview 5 lost prospects (win/loss) | High | Sales |  |  | Not Started | 0% | 03-ICP-Buyer-Research/VoC-Interviews/20260806_Secondary_VoC_Research_PublicReviews_v1.md; 20260806_Secondary_VoC_Research_SMBSurveyData_v1.md | Question bank ready — needs contact list + scheduling. Interim: 2 secondary-research passes complete (Clutch/G2/Trustpilot + SMB survey data) as a stand-in per Bridge Plan Part 1 | Pull first 10 contacts from CRM/network (5 current or ICP-fit contacts + 5 lost prospects) and send invites; target 8-10 non-customer ICP conversations per Bridge Plan
24 | VoC Research | Interview 3 churned clients | Medium | Account Mgmt |  |  | Not Started | 0% | 03-ICP-Buyer-Research/VoC-Interviews/20260806_Secondary_VoC_Research_PublicReviews_v1.md; 20260806_Secondary_VoC_Research_SMBSurveyData_v1.md | Question bank ready — needs contact list + scheduling. Interim: 2 secondary-research passes complete (Clutch/G2/Trustpilot + SMB survey data) as a stand-in per Bridge Plan Part 1 | Pull first 10 contacts from CRM/network (5 current or ICP-fit contacts + 5 lost prospects) and send invites; target 8-10 non-customer ICP conversations per Bridge Plan
25 | VoC Research | Code and synthesize interview transcripts | High | Research |  |  | Not Started | 0% |  | Dep: Tasks 22-24 | Build coding sheet
26 | VoC Research | Launch quarterly NPS survey | Medium | Account Mgmt |  |  | Not Started | 0% |  |  | Select survey tool
27 | Positioning | Draft messaging house (pillars + proof points) | High | Marketing | 2026-08-06 | 2026-08-06 | In Progress | 60% | 04-Positioning-Offers/Messaging_House_v1.md | Hypothesis-stage — refined by 2 secondary-research passes, still needs primary VoC validation | Refine with real client language from VoC interviews
28 | Positioning | Write value proposition per ICP | High | Marketing | 2026-08-06 | 2026-08-06 | In Progress | 60% | 04-Positioning-Offers/Value_Propositions_By_ICP_v1.md | Hypothesis-stage — refined by 2 secondary-research passes, still needs primary VoC validation | Refine with real client language from VoC interviews
29 | Positioning | Test messaging with 5 live prospects | Medium | Sales |  |  | Not Started | 0% |  | Blocked until 5 live prospect conversations available | Run once VoC/sales calls begin
30 | Offer Design | Design package tiers — Digital Marketing | High | Founder | 2026-08-06 | 2026-08-06 | In Progress | 85% | 04-Positioning-Offers/Package_Pricing_AllServiceLines_v2.md | Real competitor data now in hand — reduced to a founder lane decision (see v2 doc), not a research gap | Founder picks Lane A/B per v2 doc's explicit options
31 | Offer Design | Design package tiers — IT Services | High | Founder | 2026-08-06 | 2026-08-06 | In Progress | 90% | 04-Positioning-Offers/Package_Pricing_AllServiceLines_v2.md | Resolved via real competitor pricing data — validated, no founder decision needed | Publish v2 as final once founder does a final skim
32 | Offer Design | Design package tiers — AI & Automation | High | Founder | 2026-08-06 | 2026-08-06 | In Progress | 90% | 04-Positioning-Offers/Package_Pricing_AllServiceLines_v2.md | Resolved via real competitor pricing data — validated, no founder decision needed | Publish v2 as final once founder does a final skim
33 | Offer Design | Design package tiers — Web Development | High | Founder | 2026-08-06 | 2026-08-06 | In Progress | 90% | 04-Positioning-Offers/Package_Pricing_AllServiceLines_v2.md | Resolved via real competitor pricing data — validated, no founder decision needed | Publish v2 as final once founder does a final skim
34 | Offer Design | Design package tiers — Virtual Assistant | Medium | Founder | 2026-08-06 | 2026-08-06 | In Progress | 85% | 04-Positioning-Offers/Package_Pricing_AllServiceLines_v2.md | Real competitor data now in hand — reduced to a founder lane decision (see v2 doc), not a research gap | Founder picks Lane A/B per v2 doc's explicit options
35 | Offer Design | Design package tiers — Graphic Design | Medium | Founder | 2026-08-06 | 2026-08-06 | In Progress | 90% | 04-Positioning-Offers/Package_Pricing_AllServiceLines_v2.md | Resolved via real competitor pricing data — validated, no founder decision needed | Publish v2 as final once founder does a final skim
36 | Offer Design | Design package tiers — Video Editing | Medium | Founder | 2026-08-06 | 2026-08-06 | In Progress | 85% | 04-Positioning-Offers/Package_Pricing_AllServiceLines_v2.md | Real competitor data now in hand — reduced to a founder lane decision (see v2 doc), not a research gap | Founder picks Lane A/B per v2 doc's explicit options
37 | Offer Design | Build pricing corridors per country | High | Founder | 2026-08-06 | 2026-08-06 | Complete | 100% | 04-Positioning-Offers/Pricing_Corridors_By_Country_v1.md |  | Re-validate after first 5-10 real deals close per country
38 | Channels & Sales | Set up/clean CRM pipeline stages | High | Ops | 2026-08-06 | 2026-08-06 | In Progress | 85% | 05-Channels-Sales-Systems/Odoo_CRM_Setup_Guide_v1.md | Tool selection resolved (Odoo, already company-wide) — remaining gap is live configuration in the Odoo instance, not desk research | Implement the 8-item setup checklist in Odoo_CRM_Setup_Guide_v1.md directly in the live instance
39 | Channels & Sales | Build cold email sequence (v1) | High | Sales | 2026-08-06 | 2026-08-06 | Complete | 100% | 05-Channels-Sales-Systems/Cold_Email_Sequence_v1.md | Hypothesis-stage — unvalidated against real reply-rate data | Pilot Batch 1 (100 contacts, 1 ICP/country) per Email Testing Matrix
40 | Channels & Sales | Build LinkedIn outreach sequence (v1) | High | Sales | 2026-08-06 | 2026-08-06 | Complete | 100% | 05-Channels-Sales-Systems/LinkedIn_Outreach_Sequence_v1.md | Hypothesis-stage — unvalidated against real accept/reply-rate data | Pilot Batch 1 (100 connections, 1 ICP/country) per LinkedIn Testing Matrix
41 | Channels & Sales | Set up email domain warming/infra | High | Ops |  |  | In Progress | 40% | 05-Channels-Sales-Systems/Email_Domain_Warming_Infra_Setup_v1.md | Plan documented; requires domain purchase + mailbox setup (execution, not desk research) to progress further | Register sending domains, set up mailboxes, start Week 1 warm-up cycle
42 | Content & SEO | Complete keyword research (all countries) | High | Marketing | 2026-08-06 | 2026-08-06 | Complete | 100% | 05-Channels-Sales-Systems/Keyword_Map_By_Country.md | Desk-research hypothesis, not pulled from Ahrefs/Semrush — no live keyword tool connected yet | Connect Ahrefs/Semrush and re-pull real volume/difficulty data
43 | Content & SEO | Build pillar page structure (7 service lines) | High | Marketing | 2026-08-06 | 2026-08-06 | Complete | 100% | 05-Channels-Sales-Systems/Pillar_Article_Outlines_v1.md; 05-Channels-Sales-Systems/Pillar-Articles-FullCopy/ (full copy, all 7 + cross-cutting) | Cross-cutting pillar Section 3 still needs founder-voice narrative; illustrative examples (AI & Automation, Video Editing) need real case studies once Task 44 unblocks; not yet SEO-validated against Task 42 real keyword data | Assign editorial owner for voice/brand pass (Content_Calendar_Q1.md); founder to draft cross-cutting Section 3; schedule publish dates
44 | Content & SEO | Produce 3 case studies | High | Marketing |  |  | Blocked | 15% | 05-Channels-Sales-Systems/Case_Study_Templates_v1.md | Still requires real client interviews (Task 22) — but structure, question bank, and placement plan are now fill-in-ready, so turnaround once a client agrees is fast | Use template the moment first Closed Won deal hits the 60-day case-study-request trigger in Odoo
45 | Content & SEO | Build thought-leadership content calendar (Q1) | Medium | Marketing | 2026-08-06 | 2026-08-06 | Complete | 100% | 05-Channels-Sales-Systems/Content_Calendar_Q1.md | Topic bank is hypothesis-stage; real publish dates not yet set | Confirm kickoff month and assign owners
46 | Trust & Compliance | Draft information security policy | High | Ops |  |  | In Progress | 80% | 06-Trust-Compliance/Information_Security_Policy_v1.md | Legal review needed before external use | Route to legal counsel for review
47 | Trust & Compliance | Draft data handling policy | High | Ops |  |  | In Progress | 80% | 06-Trust-Compliance/Data_Handling_Policy_v1.md | Legal review needed, especially the 5-country regional compliance statements | Route to legal counsel for review
48 | Trust & Compliance | Build vendor security questionnaire answer bank | Medium | Ops |  |  | Complete | 100% | 06-Trust-Compliance/Vendor_Security_Questionnaire_AnswerBank.md | Cyber liability/E&O insurance gap surfaced — not yet purchased | Founder to evaluate and purchase E&O/cyber liability coverage
49 | Trust & Compliance | Finalize MSA/SOW/NDA templates | High | Founder |  |  | In Progress | 70% | 06-Trust-Compliance/MSA_Template.md; SOW_Template.md; NDA_Template.md | Legal review required; governing law/dispute-resolution jurisdiction undecided (blocks finalization even after legal review) | Founder + legal decide governing law, then complete legal review
50 | Metrics | Build executive KPI dashboard (v1) | High | Ops |  |  | In Progress | 60% | 07-Metrics-Dashboards/KPI_Definitions_Master.md; Dashboard_Tool_Spec.md (v2); Odoo_CRM_Setup_Guide_v1.md | Tool ambiguity resolved (Odoo native reporting + Looker for GA4) — still blocked on live Task 38 configuration for real data | Once Odoo CRM pipeline is configured, build the 3 Odoo Spreadsheet dashboard views per Dashboard_Tool_Spec.md v2
51 | Metrics | Define KPI owners and reporting cadence | Medium | Founder |  |  | In Progress | 60% | 07-Metrics-Dashboards/KPI_Definitions_Master.md (Reporting Cadence & Ownership section) | Ownership currently defaults to Founder per placeholder RACI — needs real names | Assign in RACI (Task 3), then update KPI ownership section with real names
52 | Governance | Schedule recurring weekly review | Medium | Founder |  |  | Not Started | 0% |  |  | Calendar invite
53 | Governance | Schedule monthly steering review | Medium | Founder |  |  | Not Started | 0% |  |  | Calendar invite
54 | Pilot Execution | Launch pilot campaign — Country 1 | High | Sales + Marketing |  |  | Not Started | 0% |  | Dep: Phases 1-6 | Define pilot scope

## Summary
Nivy Next Research — Progress Summary
Total Tasks
Not Started
In Progress
Blocked
Complete
Overall % Complete